## Munka1
User Registration and Authentication:
1. SIGN UP
|  | 2 | Fields: First name, Last name, Email (unique), Password (hashed and stored securely), Confirm Password.
|  | 1 | Basic validation (Email format check. + Password strength requirements (e.g., minimum 8 characters, at least one uppercase, one lowercase, one number).
|  | 5 | Confirmation email upon successful registration (optional, if time permits).
|  | 13 | Google + Facebook Authentication
|  | 13 | Two Factor Authentication with Email
|  | 2 | GDPR (Privacy Policy & Terms of Agreement)
|  | 0 | Dummy “Need help?” link
|  | 5 | ( Captcha )
|  | 13 | ( Magic link )
54
2. LOG IN
|  | 1 | Fields: Email, Password.
|  | 8 | JWT (JSON Web Token) or session-based authentication upon successful login.
|  | 3 | Error handling for incorrect email or password.
12
3. PASSWORD RESET
|  | 8 | Users can request a password reset link sent to their email.
|  | 8 | Temporary token generated for reset, with an expiration time.
|  | 5 | Users click on the link in the email, are directed to a reset page to provide a new password.
21
4. PROFILE PAGE
|  | 3 | Users can view and update their personal details.
|  | 8 | Name, list of billing & shipping addresses, nickname, photo upload
|  | 5 | Purchase history
|  | 2 | Change password option.
18
Product Display
1. PRODUCT CATEGORIES
|  | 8 | 3 level category structure
|  | 8 | Highlighted products (manually from admin or based on traffic (e.g. top 10% of products are highlighted))
16
2. PRODUCT LISTING
|  | 2 | Display product image, name, price, and a short description.
|  | 13 | Pagination functionality.
|  | 13 | Sort and filter options (e.g., by price, category). (Preset quick filter & sort (e.g. from lowest price / most popular / highest reviewed))
28
3. PRODUCT DETAIL PAGE
|  | 8 | Detailed description that looks like a sub webpage
|  | 5 | Larger product image that can be zoomed & panned
|  | 3 | Product specs
|  | 2 | Option to add to cart.
|  | 21 | Price tracker (email notification) as a routine script (e.g. 3x daily)
|  | 13 | Questions & Answers
|  | 13 | Estimated shipping date (different options)
|  | 5 | Add to favorites (with folders)
|  | 5 | Product versions (red/black, 16/64GB)
75
4. PRODUCT REVIEWS
|  | 5 | Users can submit reviews (up to 5 stars)
|  | 8 | Pagination
|  | 2 | Average rating
|  | 3 | 1-5 scale (how many 1’s, 5’s etc.)
|  | 1 | How many people recommend the product (%)
|  | 5 | Attach photo
|  | 5 | Filter & sort reviews
|  | 5 | Text search
34
5. SEARCH FUNCTIONALITY
|  | 5 | Allow users to search products by name or category.
|  | 5 | Display search results in the product listing format.
|  | 5 | Real time results.
15
Shopping Cart
1. CART OVERVIEW
|  | 5 | List products added to the cart with image, name, quantity, price, and total price.
|  | 3 | Show free shipping threshold
|  | 13 | Show top product as recommendation from connected category
|  | 2 | Option to remove a product or adjust quantity.
|  | 1 | Display total price for all items.
|  | 5 | Apply simple % discount coupon on total cart value + coupon market research
29
2. CHECKOUT BUTTON
|  | 1 | Leads to the checkout page if the user is logged in.
|  | 1 | Leads to the login/sign-up page if the user is not authenticated.
2
Checkout
1. DELIVERY ADDRESS
|  | 2 | Select or add new billing & shipping address
|  | 8 | Select shipping mode (in store, shipping, GLS pont)
|  | 1 | Select payment mode (credit card / bank transfer / on receipt)
11
2. PAYMENT METHOD
|  | 13 | Integration with a payment gateway (Barion / Simple).
13
3. ORDER SUMMARY
|  | 2 | Display all products, quantities, individual prices, and total price.
|  | 1 | Confirm button to finalize the order.
3
4. CONFIRMATION
|  | 1 | Display a confirmation message upon successful order placement.
|  | 2 | Accepts Terms of Use & GDPR & subscribe to newsletter
|  | 2 | Send an email confirmation.
5
5. INVOICE GENERATION
|  | 8 | Custom PDF invoice sent in email
|  | 13 | Optionally connect with http://Szamlazz.hu / Billingo API
21
Order History
1. LIST OF ORDERS
|  | 2 | Display order number, date, total amount, and status (e.g., processing, shipped, delivered).
|  | 1 | PDF invoice
|  | 2 | Check live order states (e.g. gathering from supplier, under shipping)
5
2. ORDER DETAIL
|  | 2 | Click on an order number to view detailed information including products, quantities, total price, delivery address, and payment method used.
2
Admin Panel
1. LOGIN
|  | 5 | Separate admin login (different from users).
|  | 3 | Dashboard overview displaying number of orders, registered users, and total sales.
8
2. PRODUCT MANAGEMENT
|  | 2 | Add new products with fields: name, description, price, image upload, category.
|  | 1 | Edit existing product details.
|  | 1 | Delete products.
|  | 2 | Manage and reply to reviews.
6
3. ORDER MANAGEMENT
|  | 2 | View all orders.
|  | 2 | Update order status.
|  | 1 | View order details including delivery address and payment method.
5
4. USER MANAGEMENT
|  | 2 | CRUD user data
|  | 1 | Ban/unban or deactivate user accounts.
3
| TOTAL | 386 | 1212.04
|  |  | 488 | beletolt órák
|  |  | 7.4511 | projekthossz
| REDUCED I. | 285 | 894.9
|  |  | 754 | beletolt órák
|  |  | 3.5606 | projekthossz
Reduced verzió esztimált befejezése 2024. január 21-én.